## Slide 1
Sign-in .........................................................
Welcome & Opening Prayer………….…….
Agenda Items:
1. Purpose of meeting: BHM 2015
2. Facts----WWWWW & HM
3. Discuss/Vote on Entertainment and Guest Speaker
4. Review & Confirm Areas of Responsibility/Commitment
5. Issue Event Tickets
  Way Ahead: Next Meeting(s)…… 14 Jan 2015
  4 Feb 2015---Pre-execution meeting… turn-in ticket money and unsold tickets.
  7 Feb 2015---CSO’s 4th Annual Black History Month Program.
  18 Feb 2015---CSO quarterly meeting
Closing Prayer ...........................................
Community Service Organizations’ BLACK History Month (BHM) Planning and Coordination Meeting
Richard Allen Cultural Center
Wednesday, December 17, 2014
6:30PM

## Slide 2
Program /Protocol/Entertainment---CSO XOs/DST
Find a Guest Speaker/Decide on Theme
Designate EMCEE
Create sequence/Secure info for program/introductions etc.
Coordinate with Hospitality for VIP/entertainer seating areas.
Print Programs.
Coordinate layout of rooms with RFCC Staff (seating, podium, piano, stage and dance floor, DJ, coat check, etc.)
Get the liquor license to sell drinks
Ticket Broker---APA & RACC&M
Distribute and account for sold and unsold tickets.
Collect money for tickets sold.
Prepare report of total sales and money received.
Coordinate with Hospitality (as required).
Food---Socialite Club & Les Novelettes
Coordinate with caters for meats.
Task out menu items.
Stay within the food budget.
Provide food servers.
Setup, display and serve the food.
Keep buffet line replenished, refreshed.
Bar---OPP
Purchase spirits and supplies.
Setup and operate bar.
Account for sales/taxes.
Recover and pack up leftover bar items.
Hospitality/Ushers/Seating/ Protocol---MAS
Manage/Control Seating at the Event
Provide Ushers and Greeters
Provide People to Work the Ticket Table
Receive and seat VIPs and entertainers.
Sell Event Tickets---ALL
Set-up/Layout/Breakdown/Load Out –DPC &
(One Rep from Each Organization)
Decorate banquet tables.
Decorate guest tables. Set-up the Venue.
BHM Exhibits---
Solicit and organize organizational displays in the Women’s Room.
Publicity/Signage---
Publicize event in print and social media.
Create informational signs for venue.
Raffle---OES
Solicit prizes
Set-up and operate raffle table.
BLACK HISTORY MONTH PROGRAM 2015
Committees